## Slide 1: Recruiting, Screening and Testing High School Youth for Apprenticeships

## Slide 2: Youth Pre-Apprentice Recruiting, Screening and Testing
Educator Awareness
Recruiting
Applicant Review
College Placement
Mentor Training
Orientation
Testing
Pre Apprenticeship
Signing Ceremony

## Slide 3: Process Timeline

## Slide 4: Educator Awareness - October
Educator awareness luncheon
CTE teachers and principals at targeted schools
Hosted by sponsor companies at a partner facility with a tour
Recruiting – December
Facility tours on a Saturday (Open House)
Students and parent/guardian must attend the facility tour

## Slide 5: Recruiting – January & February
Recruiting at targeted high schools by sponsor companies
College Placement Testing - Feb.
Student takes college placement test
It is the student’s responsibility to schedule and take the placement test
Student supplies placement test scores to sponsor company

## Slide 6: Orientation and Testing - Example
The following example is customized for advanced manufacturing but can easily be adapted to other sectors such as healthcare or IT.
The content should match the skills needs of area employers.

## Slide 7: Orientation and Testing - April
Day 1
  Review agenda for week
  Discuss and sign rules contract
  Technical math
  Metric to standard conversion methods
  Homework assignment
  Measuring tools

## Slide 8: Orientation and Testing – April
Day 2
  Project commencement
  Hand filing
  Light machining under close supervision
  Sandblasting
  Hand Tapping
Day 3
  Project completion
  Final assembly
  Project evaluation
  1st/3rd angle projections

## Slide 9: Orientation and Testing
Day 4
Testing
  Ramsey Mechanical Aptitude
  Custom Tests
  Predictive Index
Rankings
  Student ranks companies for pre-apprentice program

## Slide 10: Mentor Training – May
Mentor training for operators that will serve as Apprenticeship Mentors (12 hours)

## Slide 11: Pre-Apprentice – June & July
6 Weeks
  No obligations week of July 4th
2 Classes at Community College
  Industry safety
  Intro to engineering
Employer placement
  40 hour work week
  Employer-paid

## Slide 12: Signing Ceremony – August
Sponsors arrange a ceremony with presentations
Apprentices, parents and community leaders/dignitaries are invited

## Slide 13: Apprenticeship – August
Full apprenticeships begin at the end of August

## Slide 14: Contact Us
Pam Howze Program Director National Fund for Workforce Solutions phowze@nationalfund.org
info@nationalfund.org www.nationalfund.org TEL 202.223.8994 1730 Rhode Island Ave. Suite 712 Washington DC, 20036